## Status Report
Project Name | Top Down Zelda-esque Game |  | Date |  | 2024-10-12 | Project Manager |  | Sarah Beecroft
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
The goal is, as the name implies, a top-down puzzle game inspired by the Legend of Zelda. Utilizing Unreal Engine, this game will employ a 3D top down style, similar to the Nintendo Switch version of Link's Awakening. There will be the main character you play as, along with their moveset, enemies to fight, an NPC to interact with, and basic dungeon and play mechanics and UI elements. |  |  |  | UI |  | 10% | Possible Delays
|  |  |  | Interactable objects/items |  | 50% | On Track
|  |  |  | Enemy implementation |  | 40% | On Track
|  |  |  | Camera movement |  | 0% | Future Task
|  |  |  | Modelling |  | 85% | On Track
|  |  |  | Puzzle design and implementation |  | 40% | On Track
|  |  |  | Animation |  | 0% | Future Task
[6 empty] | 0% | Future Task
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
Heart and key counter Teleport functionality | [5 empty] | Modelling Pot interaction Block pushing gimmick Level design
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Sarah Beecroft | Pot interaction | 3 | Issue | Most of us are still learning Unreal, which may cause issues with task completion and deadlines.
Tanner Hartwell | level design | 4
Khai Hirschi | Enemy behavior | 4
Devon Gneiting | Modelling | 4 | Issue | Version control for Unreal isn't as simple as Git, due to Unreal's high number of binary files and amount of space it takes up
George Li | Push block/teleport | 4
Derek |  | N/R
Total |  | 19

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task