## Status Report
Project Name | Top Down Zelda-esque Game |  | Date |  | 2024-11-16 | Project Manager |  | Sarah Beecroft
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
The goal is, as the name implies, a top-down puzzle game inspired by the Legend of Zelda. Utilizing Unreal Engine, this game will employ a 3D top down style, similar to the Nintendo Switch version of Link's Awakening. There will be the main character you play as, along with their moveset, enemies to fight, an NPC to interact with, and basic dungeon and play mechanics and UI elements. |  |  |  | UI |  | 60% | Delayed
|  |  |  | Interactable objects/items |  | 95% | On Track
|  |  |  | Enemy implementation |  | 100% | Complete
|  |  |  | Puzzle implementation |  | 100% | Complete
|  |  |  | Modelling |  | 100% | Complete
|  |  |  | Level design |  | 100% | Complete
|  |  |  | Animation |  | 100% | Complete
[6 empty] | 0% | Future Task
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
Animations Finish enemy implementation Finalize level design Finish pot implementation UI
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Sarah Beecroft | Pot interaction | 6 | Issue | Most of us are still learning Unreal, which may cause issues with task completion and deadlines.
Tanner Hartwell | Bugs and UI | 4
Khai Hirschi | Finishing enemies | 2
Devon Gneiting | Animating and textures | 5 | Issue | Version control for Unreal isn't as simple as Git, due to Unreal's high number of binary files and amount of space it takes up
George Li | Finishing map design | 2
Derek McKinley | N/A | 1.5
Total |  | 20.5

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task